## Daily Status Reporting
Daily Status Report
Legend
Date | 27-04-2020 |  | Status on track
Resource Name |  |  | Slight deviation
Reporting Manager |  |  | Not on track. Need attention
Tasks Execution Completion Status
Tasks Planned | Tasks Executed(yes/No) | Tasks Execution Status | Execution Effort(Hrs) | Complete (%) | Comments
User Module-Front end | No | Pending | 3 | 70
Registration Module | Yes | Finished | 3 | 100